## Finetuning LLMs for CTI (Cyber Threat Intelligence) Domain.

## Objective

The primary objective of this project is to fine-tune Large Language Models (LLMs) specifically for the CTI domain. This will involve systematically gathering, preprocessing, and transforming diverse structured and unstructured cybersecurity datasets into formats suitable for model fine-tuning. The goal is to enhance the model’s domain-specific capabilities to understand, analyze, and process CTI-related information effectively.

As agreed with you, the project is designed to be executed on a fixed-cost, milestone-based approach, with defined deliverables at each stage.

Milestone 1: Data Collection, Assessment & Usefulness Analysis

Step 1: Data Gathering and Understanding

Data Sources:

| Data Type | Count | Formats/Methods |
| --- | --- | --- |
| Structured | 7 | JSON, CSV, STIX |
| Unstructured | 5 | RSS Feeds (1), PDF (2), Web Scraping (2) |

- Tools to Scrap the data

- Data Gathering:  Collect the data from the identified sources using appropriate methods:

  - API-based data pulling.

  - Manual extraction where automation is not feasible.

  - Writing codes for web scraping wherever applicable.

  - Understanding the data definition and data dictionary.

  - Understanding the relationship among various elements within structured data.

- Data Usefulness Understanding: Assess the relevance and applicability of the collected data by analyzing:

  - Whether the data contains domain-specific information required for model fine-tuning.

  - If the data can be mapped to relevant cybersecurity concepts such as vulnerabilities, attack techniques, or threat actors.

  - Whether the data needs additional processing, such as translation, normalization, or enrichment.

  - Suitability of the data for transforming into fine-tuning formats, including blog-style narratives, Q&A pairs, or structured knowledge entries.

Deliverables:

- Report on Quality of Dataset and their usefulness.

- Report on data cleaning and preprocessing needed.

Milestone 2: Data Cleaning, Preparation & Model Planning

Step 1: Data Cleaning Preprocessing:

- Clean the collected datasets by removing duplicates, inconsistencies, and irrelevant fields.

- LM-based Filtering (if applicable): Remove irrelevant, noisy, or out-of-domain content using pre-trained language models. For example:

    - Translate or remove non-english data whichever is applicable.

    - Removing Garbage data from the data source such as removing table of content, appendix, and other irrelevant fields.

- Heuristic Filtering: Apply rule-based filtering methods for additional data cleaning.

Step 2: Data Preparation:

For each data source, we will prepare data in a format useful for fine-tuning the model for domain knowledge. For example:

- Converting the structured data  (MITRE, CAPEC etc) into Blog or information style format for model finetuning.

- Handling Vulnerable data into model finetuning format.

- Creating some synthetics data in terms of Q&A for task related understanding of the model

Step 3: Model Architecture Strategy Planning

We will plan the initial model design strategy:

- Model List Identification: Identify suitable pre-trained models that can be adapted for the project (including pretrained CTI-specific models if applicable).

- Pretraining vs. Fine-tuning Assessment: Evaluate the need for additional pretraining versus direct instruction for fine-tuning.

- Framework Selection: Identify frameworks and tools to be used for training (with preference for Hugging Face-compatible solutions).

- Training Platform Identification: Recommend cloud-based or on-premises platforms suitable for fine-tuning and experimentation (e.g., RunPod).

Note: Data cleaning steps will be performed as needed in the data source and will not be performed where needed.

Deliverables:

- Cleaned Datasets for Model Finetuning

- Codebase for Data cleaning and preprocessing

- List of Models that can be used for finetuning, Platform and framework for finetuning.

- Infrastructure recommendations (cloud/on-premises) for training.

Milestone 3: Model Fine-Tuning, Infrastructure Setup & Performance Evaluation

#### 1. Codebase & Infrastructure Setup

- Set up the required development environment and codebase for model fine-tuning using Hugging Face libraries and frameworks.

- Configure necessary libraries, dependencies, and utilities for:

  - Parameter-Efficient Fine-Tuning (PEFT) techniques such as LoRA, QLoRA, or similar methods.

  - Tokenization, data loaders, training scripts, and evaluation pipelines.

- Provision the necessary cloud-based or on-premises infrastructure for fine-tuning experiments, such as:

  - RunPod, Hugging Face Inference Endpoints, or custom cloud instances (depending on client preference and project needs).

- Document the full environment configuration for reproducibility.

#### 2. Model Fine-Tuning (Domain-Specific Adaptation)

- Fine-tune a pre-trained LLM (Selected framework in Milestone 1) to adapt it for domain-specific knowledge in CTI.

  - Load the cleaned, structured datasets from Milestone 1.

  - Apply PEFT techniques for efficient fine-tuning.

  - Train and validate the model using the prepared datasets.

  - Tune key hyperparameters (learning rate, batch size, number of epochs, etc.) to optimize performance.

#### 3. Model Evaluation & Benchmarking

- Evaluate the fine-tuned model using standard open-source benchmarks relevant to the CTI or cybersecurity domain.

- Assessment criteria may include:

  - Perplexity / Loss metrics.

  - Benchmark Specific metrics.

#### 4. Reporting & Deliverables

- Prepare a comprehensive report summarizing:

  - Fine-tuning methodology and configurations used.

  - Infrastructure setup and environment details.

  - Dataset utilization and processing summary.

  - Model performance metrics and benchmark results.

- Deliverables for this milestone:

  - Fine-tuned model files and code repositories.

  - Configuration and environment documentation.

  - Final evaluation report.

### Project Deliverables by Milestone

| Milestone | Deliverables | Time Estimate | Considering Parallel Resources |
| --- | --- | --- | --- |
| Milestone 1: Data Collection, Assessment & Usefulness Analysis | - Report on Quality of Dataset and their usefulness. - Report on data cleaning and preprocessing needed. - Data Dictionary & Relationship Mapping (for structured data). | 58 Days | 16 Days |
| Milestone 2: Data Cleaning, Preparation & Model Planning | - Cleaned Datasets for Model Finetuning - Codebase for Data cleaning and preprocessing - List of Models that can be used for finetuning, Platform and framework for finetuning. - Infrastructure recommendations (cloud/on-premises) for training. | 100.5 days | 21 Days |
| Milestone 3: Model Fine-Tuning, Infrastructure Setup & Performance Evaluation | - Fine-tuned model files and code repositories. - Configuration and environment documentation. - Final evaluation report. | 18 Days | 18 Days |
|  | TOTAL DAYS | 177 Days | 55 Days |

Final Estimate for Milestone 1:

| Task | Time Estimate | Considering Parallel Resource | Cost Estimate (in $) |
| --- | --- | --- | --- |
| Data Collection Assessment & Usefulness Analysis | 48 Days | 12 Days (4 Resource) | 9600 |
| Supervision | 2 Days | 2 Days | 480 |
| Buffer Time | 8 Days | 2 Days (4 Resource) | 1600 |
|  |  | TOTAL | 11680 |

Note: Considering the nature of data sources, their availability, and constraints, we have included buffer time of 8 days, which is applicable if additional time is needed.

Final Estimate for Milestone 2:

| Task | Time Estimate | Considering Parallel Resource | Cost Estimate (in $) |
| --- | --- | --- | --- |
| Data Collection Assessment & Usefulness Analysis | 100.5 Days | 21 Days (5 Resources) | 20100 |
|  |  | TOTAL | 20100 |

Note: Based on the outcome of Milestone 1, the time estimates of the 2nd milestones can change, that will be reevaluated if applicable.

Final Estimate for Milestone 3:

| Task | Time Estimate | Considering Parallel Resource | Cost Estimate (in $) |
| --- | --- | --- | --- |
| Data Collection Assessment & Usefulness Analysis | 15 Days | 15 Days (1 Resource) | 3600 |
| Buffer Time | 3 Days | 3 Days (1 Resource) | 720 |
|  |  | TOTAL | 4320 |

Note: Based on the outcome of Milestone 1, 2 and size and complexity of the data, the time estimates of the 3rd milestones can change, that will be reevaluated if applicable.

Total Estimate

| Milestones | Cost including buffer(in $) | Cost without Buffer (in $) |
| --- | --- | --- |
| Milestone 1 | 11680 | 10080 |
| Milestone 2 | 20100 | 20100 |
| Milestone 3 | 4320 | 3600 |
| Total | 36100 | 33780 |

Appendices:

Milestone 1: Data Sources are in different formats like GitHub Repositories, Blogs, Links, PDFs. We need to figure out tools for web scraping; we need to write custom codes for web scraping.

Note:

1. Based on the outcome of Milestone 1, the time estimates of the next milestones can change, that will be reevaluated if applicable.

2. Based on our analysis so far, some known complexities in data sources are as follows:

- MISP galaxy Data Source: The MISP Galaxy dataset includes descriptions in different languages, which requires preprocessing. We will need to translate non-English text and filter it to ensure consistency and relevance for further analysis and fine-tuning.

- APT Notes: APT Notes are mostly PDF reports containing detailed threat intelligence, including diagrams, charts, and images. Extracting useful information from these PDFs will require careful handling of both text and visual elements to retain full context.

- CTI Blogs/ Exploit DB: Some blogs and exploit databases contain important command-line data embedded as images instead of text. Extracting this information accurately will require web scraping along with OCR techniques to ensure that critical technical details are not lost.

- Zero Day Initiatives: ZDI advisories are provided in RSS format, which requires parsing and conversion into a structured format. Additional steps will be needed to fetch detailed advisory content from external links for complete data extraction.

- Google Project Zero: Vulnerability advisories from Google Project Zero are hosted as unstructured web pages, requiring targeted web scraping and data parsing to collect and organize relevant cybersecurity information.

3.  Efforts Time calculation

| Data Source | Download / Web Scraping | Usefulness Data Understanding | Data Dictionary Understanding | Relationship Understanding | Data Preprocessing Understanding | Documentation | Total Days required |
| --- | --- | --- | --- | --- | --- | --- | --- |
| MITRE ATT&CK | 0.5 | 1 | 0.5 | 1 | 1 | 0.5 | 4.5 |
| CAPEC | 1.5 | 0.5 | 0 | 0.5 | 1 | 0.5 | 4 |
| MISP-Galaxy | 0.5 | 0 | 1 | 1 | 1 | 0.5 | 4 |
| MISP-Texonomies | 0.5 | 0.5 | 1 | 0 | 1 | 0.5 | 3.5 |
| GOOGLE PROJECT ZERO | 2 | 0 | 1 | 0 | 1 | 0.5 | 4.5 |
| CWE | 0 | 1 | 0 | 1 | 1 | 0.5 | 3.5 |
| CVE | 0 | 0 | 1 | 1 | 1 | 0.5 | 3.5 |
| ZDI | 0.5 | 1 | 0 | 1 | 1 | 0.5 | 4 |
| THREATFOX IOC | 1.5 | 0 | 1 | 0.5 | 1 | 0.5 | 4.5 |
| APT NOTES | 2 | 0.5 | 0 | 0 | 1 | 0.5 | 4 |
| CTI BLOGS | 2 | 0 | 0.5 | 0 | 1 | 0.5 | 4 |
| Exploit DB | 2 | 0 | 0.5 | 0 | 1 | 0.5 | 4 |
| Buffer Time |  |  |  |  |  |  | 10 |
|  |  |  |  |  | TOTAL DAYS |  | 58 |

4. Assumptions & Uncertainties that might occur:

- Data Accessibility: Assumes all data sources remain accessible; delays may occur if approvals or access issues arise.

- Format Consistency: Estimates are based on current formats; unexpected variations may increase effort.

- Manual Work: Web scraping estimates assume minimal restrictions; extra effort may be needed for complex sites.

- Multilingual Data: Time for translation is estimated; more effort may be required if more non-English data is found.

- Documentation Availability: Assumes basic documentation exists; missing or unclear documentation may need extra analysis.

- Data Overlaps: Some sources may overlap, requiring additional deduplication.

- Scope Stability: Estimates assume no additional datasets or scope changes during this milestone.

MILESTONE 2:

1. Based on the outcome of Milestone 1, the time estimates of the next milestones can change, that will be reevaluated if applicable.

2. We will have to assess the complexity after the outcome of Milestone 1 for data processing and cleaning.

3. Efforts Time calculation

| Tasks | Filtering | Deduplication | Garbage Removing | Heuristic Filtering | Dataset Preparation | Intra Corelationship | Q&A Data Preparation | Days Required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MITRE ATT&CK |  | 1 | 1 | 1 | 2.5 | 1 | 2 | 8.5 |
| CAPEC | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 7.5 |
| MISP-Galaxy | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 7.5 |
| MISP-Texonomies | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 7.5 |
| GOOGLE PROJECT ZERO | 1 | 1 | 1 | 1 | 2.5 | 1 | 2 | 8.5 |
| CWE | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 7.5 |
| CVE | 1 | 1 | 1 | 1 | 2.5 | 1 | 2 | 8.5 |
| ZDI | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 7.5 |
| THREATFOX IOC | 1 | 1 | 1 | 1 | 2.5 | 1 | 1 | 7.5 |
| APT NOTES | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 7 |
| CTI BLOGS | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 7 |
| Exploit DB | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 8 |
| Model Selection |  |  |  |  |  |  |  | 2 |
| Pretraining vs. Fine-tuning Assessment |  |  |  |  |  |  |  | 2 |
| Framework Selection |  |  |  |  |  |  |  | 2 |
| Training Platform Identification |  |  |  |  |  |  |  | 2 |
|  |  |  |  |  | TOTAL DAYS |  |  | 100.5 |

MILESTONE 3:

1. Based on the outcome of Milestone 1, the time estimates of the 3rd milestone can change, that will be reevaluated if applicable.

2. We are considering that evaluation datasets will be provided by you.

3. And Based on the tasks in the evaluation the time can vary.